## Sheet1
	Estimate	Done	To Do	Workload Per Week			Anna	Pierre	Selim	Sjors	Tomek	Wen
All time estimates are in hours	203	189	8	Err:511		Work done:	40	8	29	22	75	15
						Minimal work required till now:	#VALUE!	#VALUE!	#VALUE!	#VALUE!	#VALUE!	#VALUE!
Project GitHub Page	Issues	Code	Sketchpad	Work Timeline		Missing from required above:	#VALUE!	#VALUE!	#VALUE!	#VALUE!	#VALUE!	#VALUE!
						Estimated workload per week to complete:	Err:511	Err:511	Err:511	Err:511	Err:511	Err:511
						Recommended work for this week:	#VALUE!	#VALUE!	#VALUE!	#VALUE!	#VALUE!	#VALUE!
Task	Estimate	Assignee	Time spent	Comments
Project Analysis	4	Tomek	4			Weeks to go:	0
Time and tasks managment - this sheet etc.	4	Tomek	4			Start (30/10/2018):	#VALUE!
Mentoring (live coding etc.)	2	Tomek	2			Current:	50
						End (11/12/2018):	46
Starting with SWING	4	Anna	4			Deadline (14/12/2018) ...
Starting with SWING	4	Pierre	4
Starting with SWING	4	Selim	4
Starting with SWING	4	Sjors	4
Starting with SWING	4	Tomek	4
Starting with SWING	4	Wen	4

Finding tutorials and examples for the group (exact algorithm, timer, graph coloring, file chooser)	3	Tomek	3

Managing layouts (visual arangment of components)	2	Tomek	2

Selection of the game modes	2	Selim	2
Switching from game modes to graph specification	1	Tomek	1	Did not end up in the final game.

Asking for random graph specification	3	Selim	7
Asking for a graph file location	3	Selim	7
Graph file selection filtering (only txt files)	2	Selim	5
Graph specification validation (wrong format, wrong numbers etc.)	2	Tomek	1

Random graph generation	1	Tomek	1	Done in phase 1
Line graph generation	1	Wen	3	Not integrated.
Loading a graph from a file	1	Tomek	1	Based on Kelk code
Integrating graph making with graph specification screen	3	Tomek	3

Exact algorithm research	2	Tomek	2
Exact algorithm improvement	24	Anna	24	Done.
Exact algorithm integration	3	Tomek	3
Graph class	2	Tomek	4

Displaying a graph (vertices and edges, arrangement in space)	8	Anna	8
Optimizing space aragment of vertices and edges	1	Tomek	1
Displaing the required graph (integration with graph selection)	2	Tomek	2
Selecting a color	6	Sjors	6
Indicating selected color	1	Tomek	1
Adding a color	2	Sjors	8	Finally not used.
Changing a color of a vertex	4	Tomek	4
Integrating graph class with colors managment	2	Tomek	2
Display the count of the colors used (lower left corner)	2	Tomek	1

Timer counting down sketch	4	Wen	4
Timer counting down	4	Tomek	1
Timer counting up	2	Tomek	2
Integrating Timer into Graph Screen	2	Tomek	2

Main Screen Integration (graph, colors, timer)	6	Tomek	6
Fixing issues with look and feel and graph panel size on Mac	1	Tomek	1

"Bitter End" End of the game check (chromatic number found)	4	Tomek	1
"Upper bound" End of the game check (times up)	4	Tomek	1
"Upper bound" End of the game check (fully collored)	1	Tomek	1

"Random order" mode flow - allowing to color only current vertex	4
Maintaing a state of what vertex is next in "random order" mode	2

All Screens Integration	4	Tomek	1
Score and back to selection of the game modes	2	Tomek	1
"Restart game" button + action	2	Tomek	1

Show chromatic number hint	1	Tomek	1
Start validating edges hint	3	Tomek	1

Computing hints	4	Tomek	1
Displaying a hint for a "bitter end" and "upper bound"	4	Tomek	1
Displaying a hint for a "random order"	4	Tomek	1

Documentation	2	Tomek	2
Unit tests	2	Tomek

Presentation	4	Anna	4
Presentation	4	Pierre	4
Presentation	4	Selim	4
Presentation	4	Sjors	4
Presentation	4	Tomek	4
Presentation	4	Wen	4