## Sheet1
| Estimate | Done | To Do | Workload Per Week |  | Anna | Pierre | Selim | Sjors | Tomek | Wen
All time estimates are in hours | 203 | 189 | 8 | 8 | Work done: | 40 | 8 | 29 | 22 | 75 | 15
[5 empty] | Minimal work required till now: | 24 | 24 | 24 | 24 | 24 | 24
Project GitHub Page | Issues | Code | Sketchpad | Work Timeline | Missing from required above: | -16 | 16 | -5 | 2 | -51 | 9
[5 empty] | Estimated workload per week to complete: | 2 | 2 | 2 | 2 | 2 | 2
[5 empty] | Recommended work for this week: | 2 | 18 | 2 | 4 | 2 | 11
Task | Estimate | Assignee | Time spent | Comments
Project Analysis | 4 | Tomek | 4 |  | Weeks to go: | 0
Time and tasks managment - this sheet etc. | 4 | Tomek | 4 |  | Start (30/10/2018): | 44
Mentoring (live coding etc.) | 2 | Tomek | 2 |  | Current: | 50
[5 empty] | End (11/12/2018): | 50
Starting with SWING | 4 | Anna | 4 |  | Deadline (14/12/2018) ...
Starting with SWING | 4 | Pierre | 4
Starting with SWING | 4 | Selim | 4
Starting with SWING | 4 | Sjors | 4
Starting with SWING | 4 | Tomek | 4
Starting with SWING | 4 | Wen | 4
Finding tutorials and examples for the group (exact algorithm, timer, graph coloring, file chooser) | 3 | Tomek | 3
Managing layouts (visual arangment of components) | 2 | Tomek | 2
Selection of the game modes | 2 | Selim | 2
Switching from game modes to graph specification | 1 | Tomek | 1 | Did not end up in the final game.
Asking for random graph specification | 3 | Selim | 7
Asking for a graph file location | 3 | Selim | 7
Graph file selection filtering (only txt files) | 2 | Selim | 5
Graph specification validation (wrong format, wrong numbers etc.) | 2 | Tomek | 1
Random graph generation | 1 | Tomek | 1 | Done in phase 1
Line graph generation | 1 | Wen | 3 | Not integrated.
Loading a graph from a file | 1 | Tomek | 1 | Based on Kelk code
Integrating graph making with graph specification screen | 3 | Tomek | 3
Exact algorithm research | 2 | Tomek | 2
Exact algorithm improvement | 24 | Anna | 24 | Done.
Exact algorithm integration | 3 | Tomek | 3
Graph class | 2 | Tomek | 4
Displaying a graph (vertices and edges, arrangement in space) | 8 | Anna | 8
Optimizing space aragment of vertices and edges | 1 | Tomek | 1
Displaing the required graph (integration with graph selection) | 2 | Tomek | 2
Selecting a color | 6 | Sjors | 6
Indicating selected color | 1 | Tomek | 1
Adding a color | 2 | Sjors | 8 | Finally not used.
Changing a color of a vertex | 4 | Tomek | 4
Integrating graph class with colors managment | 2 | Tomek | 2
Display the count of the colors used (lower left corner) | 2 | Tomek | 1
Timer counting down sketch | 4 | Wen | 4
Timer counting down | 4 | Tomek | 1
Timer counting up | 2 | Tomek | 2
Integrating Timer into Graph Screen | 2 | Tomek | 2
Main Screen Integration (graph, colors, timer) | 6 | Tomek | 6
Fixing issues with look and feel and graph panel size on Mac | 1 | Tomek | 1
"Bitter End" End of the game check (chromatic number found) | 4 | Tomek | 1
"Upper bound" End of the game check (times up) | 4 | Tomek | 1
"Upper bound" End of the game check (fully collored) | 1 | Tomek | 1
"Random order" mode flow - allowing to color only current vertex | 4
Maintaing a state of what vertex is next in "random order" mode | 2
All Screens Integration | 4 | Tomek | 1
Score and back to selection of the game modes | 2 | Tomek | 1
"Restart game" button + action | 2 | Tomek | 1
Show chromatic number hint | 1 | Tomek | 1
Start validating edges hint | 3 | Tomek | 1
Computing hints | 4 | Tomek | 1
Displaying a hint for a "bitter end" and "upper bound" | 4 | Tomek | 1
Displaying a hint for a "random order" | 4 | Tomek | 1
Documentation | 2 | Tomek | 2
Unit tests | 2 | Tomek
Presentation | 4 | Anna | 4
Presentation | 4 | Pierre | 4
Presentation | 4 | Selim | 4
Presentation | 4 | Sjors | 4
Presentation | 4 | Tomek | 4
Presentation | 4 | Wen | 4